## Sheet1
System Name | Videogame Trading System
Members: | Rei Samson Agravante
Mikhail James Navarro
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. LOGIN
1.1. Creating UI | Mikhail James Navarro |  |  | To do
1.2. Integrate with Database | Mikhail James Navarro |  |  | To do
1.3. Password Recovery | Mikhail James Navarro |  |  | To do
2. HOMEPAGE
2.1. Price Tracking
2.1.1. Design UI | Rei Samson Agravante |  |  | In-Progress
2.1.2. Integrate API | Rei Samson Agravante |  |  | To do
3. ALERT SYSTEM | Rei Samson Agravante |  |  | To do
4. LOGOUT | Mikhail James Navarro |  |  | To do